Scope of Work & Timeline for Employee Productivity & Monitoring Application (We360.ai-like)

## 1. Project Overview

The purpose of this project is to develop a cloud-based application that enables organizations to monitor employee activity, track productivity, and optimize workforce performance. The application will be accessible via web and mobile platforms (Android & iOS) and will include AI-powered insights, reporting, and task management features.

## 2. Key Features & Modules

### A. User Management

- Employee registration, role-based access control (Admin, Manager, Employee)

- Profile management (name, contact, designation, profile picture)

- Department and team assignment

### B. Employee Monitoring

- Real-time activity tracking (application usage, websites visited, idle/active time)

- Optional live screen streaming

- Periodic screenshots capture for proof of work

- Monitoring of remote, hybrid, and in-office employees

### C. Productivity Tracking

- Categorize applications and websites as productive/unproductive

- Generate productivity scores per employee, team, and department

- AI-powered insights to identify bottlenecks and workload distribution

### D. Attendance & Time Tracking

- One-click attendance (punch-in/punch-out) via web or mobile

- Automated work hours calculation

- Absentee and leave management

### E. Task & Project Management

- Task creation, assignment, and tracking

- Project progress dashboards and status updates

- Notifications and reminders for pending tasks

### F. Reporting & Analytics

- Productivity reports by day, week, month, or custom period

- Department-wise and employee-wise dashboards

- Exportable reports (PDF, Excel)

- AI-generated suggestions to improve productivity

### G. Alerts & Notifications

- Idle-time alerts for employees

- Task deadline reminders

- Custom notifications for managers on performance anomalies

### H. Mobile Application

- Android & iOS apps for real-time monitoring and dashboards

- Push notifications for alerts and task updates

- Mobile-friendly task management

### I. Security & Compliance

- Data encryption (at rest & in transit)

- GDPR, HIPAA, SOC 2 Type II compliance

- Role-based data access and audit logs

### J. Admin Dashboard

- Overall organizational productivity overview

- Team and department management

- Configuration of productive/unproductive apps and websites

- Reports, analytics, and export options

## 3. Technical Requirements

- Frontend: React.js (Web), React Native / Flutter (Mobile)

- Backend: Python (FastAPI) / Node.js

- Database: PostgreSQL / MySQL

- Cloud Hosting: AWS / Azure / GCP

- File Storage: S3 or equivalent for screenshots/logs

- Notifications: Firebase / OneSignal

- AI/Analytics: Python ML libraries (Pandas, NumPy, scikit-learn)

## 4. Deliverables

- Fully functional web application with dashboards, monitoring, and reporting features

- Mobile applications for Android and iOS

- Admin and manager dashboards

- Documentation: user manuals, API documentation, and setup guides

- Deployment & hosting setup on cloud infrastructure

- Security and compliance reports

## 5. Timeline

| Phase | Tasks | Duration | Timeframe |
| --- | --- | --- | --- |
| Requirement Analysis & Planning | Gather requirements, define scope, prepare SRS | 2 weeks | Week 1 – 2 |
| UI/UX Design | Wireframes & mockups, dashboards, reports, approvals | 2 weeks | Week 3 – 4 |
| Backend Development | DB schema, API development, auth, productivity algorithms | 4 weeks | Week 5 – 8 |
| Frontend Development (Web) | React.js dashboard, real-time monitoring, reports | 3 weeks | Week 9 – 11 |
| Mobile App Development | Android/iOS apps, push notifications, task mgmt | 4 weeks | Week 12 – 15 |
| Integration & Testing | Backend/frontend integration, unit & system testing, bug fixes | 3 weeks | Week 16 – 18 |
| Deployment & Cloud Setup | Cloud hosting, CI/CD pipelines, security config | 1 week | Week 19 |
| Training & Documentation | User manuals, training sessions, deployment docs | 1 week | Week 20 |
| UAT & Go Live | User acceptance testing, feedback, final adjustments | 1 week | Week 21 |

Total Duration: ~21 weeks (~5 months)

## 6. Acceptance Criteria

- All modules fully functional and bug-free

- Reports and analytics accurate

- Mobile apps responsive with push notifications

- Security measures compliant with regulations

Note: Parallel development (mobile and web) can reduce total duration by 2–3 weeks. Post-launch support is not included.